## Summary
Time Estimation
Sr. No. | Features | Risk (NA/Low/Medium/High) | Type (New Request/Change Request/Bug/Missed Implementation) | Analysis/Research |  |  | Design |  |  | Development |  |  | Testing |  |  | Documentation |  |  | Feature-wise Subtotal
|  |  |  | Fixed (in hrs) | Variable (in %) | Max (in hrs) | Fixed (in hrs) | Variable (in %) | Max (in hrs) | Fixed (in hrs) | Variable (in %) | Max (in hrs) | Fixed (in hrs) | Variable (in %) | Max (in hrs) | Fixed (in hrs) | Variable (in %) | Max (in hrs) | Fixed (in hrs) | Max (in hrs)
1 | Invite Users | NA | New Request | 3 | 0% | 3 | 5 | 0% | 5 | 8 | 10% | 8.8 | 3 | 0% | 3 | 1 | 0% | 1 | 20 | 20.8
2 | User Registration | NA | New Request | 3 | 0% | 3 | 3 | 0% | 3 | 8 | 5% | 8.4 | 3 | 0% | 3 | 1 | 0% | 1 | 18 | 18.4
3 | Project/User Management | NA | New Request | 6 | 0% | 6 | 10 | 0% | 10 | 8 | 5% | 8.4 | 3 | 0% | 3 | 5 | 0% | 5 | 32 | 32.4
4 | Slack- Automate Leave Application | Medium | New Request | 15 | 20% | 18 | 2 | 0% | 2 | 40 | 15% | 46 | 13 | 0% | 13 | 8 | 5% | 8.4 | 78 | 87.4
5 | Slack- Automate Taskmail | Medium | New Request | 10 | 20% | 12 | 2 | 0% | 2 | 32 | 10% | 35.2 | 10 | 0% | 10 | 5 | 5% | 5.25 | 59 | 64.45
6 | Slack- Standup Meeting | Medium | New Request | 15 | 20% | 18 | 2 | 0% | 2 | 32 | 15% | 36.8 | 10 | 0% | 10 | 6 | 5% | 6.3 | 65 | 73.1
7 | Web Interface for Leave Application | NA | New Request | 6 | 10% | 6.6 | 6 | 10% | 6.6 | 6 | 5% | 6.3 | 2 | 10% | 2.2 | 4 | 0% | 4 | 24 | 25.7
8 | Web Interface for Task Mail | NA | New Request | 8 | 10% | 8.8 | 7 | 10% | 7.7 | 6 | 5% | 6.3 | 2 | 10% | 2.2 | 4 | 0% | 4 | 27 | 29
9 | Web Interface for Standup Meeting | NA | New Request | 7 | 15% | 8.05 | 7 | 10% | 7.7 | 6 | 2% | 6.12 | 2 | 10% | 2.2 | 4 | 0% | 4 | 26 | 28.07
10 | Deployment | NA | New Request | 10 | 30% | 13 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 | 10 | 13
|  |  | SUBTOTAL (in hrs) | 83 |  | 96.45 | 44 |  | 46 | 146 |  | 162.32 | 48 |  | 48.6 | 38 |  | 38.95 | 359 | 392.32
| Project Name | Slack Custom Integration
| Deliverables | Automated features via Slack:
1. User Registration
1. Project/Employee Mapping
2. Leave Application
3. Scrum Bot
4. Task Mail
5. Web Interface to view Details
| Start Date* | 2016-07-18
End Date*
Team Leader
NOTES
The time involved in discussion/meeting with client either on call/mail/in person is not included in the above time frame. That would be billed later.
*The start and end date of the project is in consideration of work 8 hrs per day, 5 days a week.

## Analysis&Research
Time Estimation
Sr. No. | Features | Risk (NA/Low/Medium/High) | Type (New Request/Change Request/Bug/Missed Implementation) | Analysis/Research
|  |  |  | Fixed (in hrs) | Variable (in %) | Max (in hrs)
1 | Invite Users | NA | New Request | 3 | 0% | 3
2 | User Registration | NA | New Request | 3 | 0% | 3
3 | Project/User Management | NA | New Request | 6 | 0% | 6
4 | Slack- Automate Leave Application | Medium | New Request | 15 | 20% | 18
5 | Slack- Automate Taskmail | Medium | New Request | 10 | 20% | 12
6 | Slack- Standup Meeting | Medium | New Request | 15 | 20% | 18
7 | Web Interface for Leave Application | NA | New Request | 6 | 10% | 6.6
8 | Web Interface for Task Mail | NA | New Request | 8 | 10% | 8.8
9 | Web Interface for Standup Meeting | NA | New Request | 7 | 15% | 8.05
10 | Deployment | NA | New Request | 10 | 30% | 13
|  |  | SUBTOTAL (in hrs) | 83 |  | 96.45

## Design
Time Estimation
Sr. No. | Features | Risk (NA/Low/Medium/High) | Type (New Request/Change Request/Bug/Missed Implementation) | Design
|  |  |  | Fixed (in hrs) | Variable (in %) | Max (in hrs)
1 | Invite Users | NA | New Request | 5 | 0% | 5
2 | User Registration | NA | New Request | 3 | 0% | 3
3 | Project/User Management | NA | New Request | 10 | 0% | 10
4 | Slack- Automate Leave Application | Medium | New Request | 2 | 0% | 2
5 | Slack- Automate Taskmail | Medium | New Request | 2 | 0% | 2
6 | Slack- Standup Meeting | Medium | New Request | 2 | 0% | 2
7 | Web Interface for Leave Application | NA | New Request | 6 | 10% | 6.6
8 | Web Interface for Task Mail | NA | New Request | 7 | 10% | 7.7
9 | Web Interface for Standup Meeting | NA | New Request | 7 | 10% | 7.7
10 | Deployment | NA | New Request |  |  | 0
|  |  | SUBTOTAL (in hrs) | 44 |  | 46

## Development
Time Estimation
Sr. No. | Features | Risk (NA/Low/Medium/High) | Type (New Request/Change Request/Bug/Missed Implementation) | Development
|  |  |  | Fixed (in hrs) | Variable (in %) | Max (in hrs)
1 | Invite Users | NA | New Request | 8 | 10% | 8.8
2 | User Registration | NA | New Request | 8 | 5% | 8.4
3 | Project/User Management | NA | New Request | 8 | 5% | 8.4
4 | Slack- Automate Leave Application | Medium | New Request | 40 | 15% | 46
5 | Slack- Automate Taskmail | Medium | New Request | 32 | 10% | 35.2
6 | Slack- Standup Meeting | Medium | New Request | 32 | 15% | 36.8
7 | Web Interface for Leave Application | NA | New Request | 6 | 5% | 6.3
8 | Web Interface for Task Mail | NA | New Request | 6 | 5% | 6.3
9 | Web Interface for Standup Meeting | NA | New Request | 6 | 2% | 6.12
10 | Deployment | NA | New Request
|  |  | SUBTOTAL (in hrs) | 146 |  | 162.32

## Testing
Time Estimation
Sr. No. | Features | Risk (NA/Low/Medium/High) | Type (New Request/Change Request/Bug/Missed Implementation) | Testing
|  |  |  | Fixed (in hrs) | Variable (in %) | Max (in hrs)
1 | Invite Users | NA | New Request | 3 | 0% | 3
2 | User Registration | NA | New Request | 3 | 0% | 3
3 | Project/User Management | NA | New Request | 3 | 0% | 3
4 | Slack- Automate Leave Application | Medium | New Request | 13 | 0% | 13
5 | Slack- Automate Taskmail | Medium | New Request | 10 | 0% | 10
6 | Slack- Standup Meeting | Medium | New Request | 10 | 0% | 10
7 | Web Interface for Leave Application | NA | New Request | 2 | 10% | 2.2
8 | Web Interface for Task Mail | NA | New Request | 2 | 10% | 2.2
9 | Web Interface for Standup Meeting | NA | New Request | 2 | 10% | 2.2
10 | Deployment | NA | New Request
|  |  | SUBTOTAL (in hrs) | 48 |  | 48.6

## Documentation
Time Estimation
Sr. No. | Features | Risk (NA/Low/Medium/High) | Type (New Request/Change Request/Bug/Missed Implementation) | Documentation
|  |  |  | Fixed (in hrs) | Variable (in %) | Max (in hrs)
1 | Invite Users | NA | New Request | 1 | 0% | 1
2 | User Registration | NA | New Request | 1 | 0% | 1
3 | Project/User Management | NA | New Request | 5 | 0% | 5
4 | Slack- Automate Leave Application | Medium | New Request | 8 | 5% | 8.4
5 | Slack- Automate Taskmail | Medium | New Request | 5 | 5% | 5.25
6 | Slack- Standup Meeting | Medium | New Request | 6 | 5% | 6.3
7 | Web Interface for Leave Application | NA | New Request | 4 | 0% | 4
8 | Web Interface for Task Mail | NA | New Request | 4 | 0% | 4
9 | Web Interface for Standup Meeting | NA | New Request | 4 | 0% | 4
10 | Deployment | NA | New Request
|  |  | SUBTOTAL (in hrs) | 38 |  | 38.95

## Formulae
Type |  | Risk
New Request |  | NA
Change Request |  | Low
Bug |  | Medium
Missed Implementation |  | High
1 | Invite Users | 1 Invite Users
2 | User Registration | 2 User Registration
3 | Project/User Management | 3 Project/User Management
4 | Slack- Automate Leave Application | 4 Slack- Automate Leave Application
5 | Slack- Automate Taskmail | 5 Slack- Automate Taskmail
6 | Slack- Standup Meeting | 6 Slack- Standup Meeting
7 | Web Interface for Leave Application | 7 Web Interface for Leave Application
8 | Web Interface for Task Mail | 8 Web Interface for Task Mail
9 | Web Interface for Standup Meeting | 9 Web Interface for Standup Meeting
10 | Deployment | 10 Deployment
Roshni
Ronak
Rushi
Chintan
Vishal

## Assumptions
Sr. No | Feature# | Reported Date | Reported By | Comment
1
2 |  |  | Ronak
3

## Roadblock
Sr. No | Feature# | Reported Date | Reported By | Comment

## Constraints
Sr. No | Feature# | Reported Date | Reported By | Comment